## Jun-Jul-Aug2018
Sr C4:J4No | 1 | 2 | 3 | 4 | 5 | 6 | 7
Name | Chetan | Akshay | Amruta | Sarveshwar | Nayan | Rohidas | Rakesh
Date | Activity | Activity | Activity | Activity | Activity | Activity | Activity
2018-06-22 | 1. Analysis of Authoring Tool and analysis of export/ import functionality (Till 2.00 pm). 2. Rishi(Metlife) 3. Maybe call with Sandip sir. | 1.Community 2. Walmart | 1. Luxaviation (Raju) 2. Royal Enfield (Ajinkya) | Community | 1. Coty Project 2. Community | NA | NA
2018-06-23 |  |  | Holiday
2018-06-24 |  |  | Holiday
2018-06-25 | MetLife project - Development of Module 1 | Community | 1. Luxaviation (Raju) 2. Royal Enfield (Ajinkya) | 1.KT of metlife framework from (chetan) 2.Adapt community | 1. Coty Project 2. Community
2018-06-26 | 1. Transperfect project - resolve issues 2. MetLife project - support Sarveshwar and resolve issues(if any) | 1. Community 2. Coty project | 1. Luxaviation (Raju) 2. Royal Enfield (Ajinkya) 3. Essilor Fundamentals EOA and Global(Harshita) Run time issue 4. MetLife Framework Study | 1.MetLife project | 1. Coty Project
2018-06-27 | MetLife project - support Sarveshwar and resolve issues(if any) | Walmart issues & TransPerfect - COTY Project support | 1.MetLife interactivity Development M2 | 1.MetLife M1 (suppport) 2.MetLife Interactivity development M2 | 1. Coty Project 2. Community
2018-06-28 | MetLife project - support Sarveshwar and Amruta and resolve issues(if any) | 1. TransPerfect 2. Walmart | 1.MetLife interactivity Development M2 2. Essilor Global(Issue discussion with Harshita) 3.Transperfect - COTY Project Module 4 components disscussion | 1.MetLife Interactivity development M2 | 1. Coty Project 2. Community
2018-06-29 | 1. MetLife issues | 1. TransPerfect | 1. MetLife interactivity Development | 1. MetLife | 1. Coty Project 2. Community
2018-06-30 | 1. MetLife and Community | 1. TransPerfect 2. COTY | 1. COTY Module 4 - Components. 2. MetLife 3. Royal Enfield | 1. MetLife- Issues regarding mobile interface activity. It becomes difficult to scroll long and doesn’t support to the consistency. Will be talking to Satish/ Mahesh from the development team of the vendor and will develop according to Hrishi Sir. | 1. COTY
2018-07-01 | 1. MetLife and Community | 1. Community 2. Essilor (Harshita Demo) 3. Issues Honeywell (Deepashri Project) | 1. COTY Module 4 - Components. 2. MetLife 3. Royal Enfield | 1. MetLife- Module 3 2. Meeting with Hrishi Sir and Rajesh regarding the development of the 2 apps | 1. COTY
2018-07-02 | 1. MetLife and Community | TransPerfect And COTY | 1. COTY Module 4 - Components. 2. MetLife |  | 1. COTY, 2. Community
2018-07-03 | 1. MetLife |  | Royal Enfield and MetLife |  | 1. COTY, Community
2018-07-04 | MetLife and YardStick | Community- Issue #2151 | MetLife Module 4 - Structure, Module 5 - Calculator | MetLife | 1.Community, 2.MetLife, 3.Yardstick
2018-07-05 | MetLife and YardStick | YardStick and Community | Valoptec (Harshita) and MetLife | MetLife (Component) | 1.YardStick and 2. SEBMAN
2018-07-06 | YardStick and if possible MetLife | YardStick | Valoptec (Harshita) and MetLife | MetLife (Component) | YardStick
2018-07-07 |  |  | Holiday
2018-07-08 |  |  | Holiday
2018-07-09 | 1. Import/Export Adapt Authorng Tool. 2. MetLife | 1. Available. 2. TransPerfect components if possible. 3. YardStick - Div Component review | Valoptec (Harshita) and MetLife( Module 3 delivery EOD, Module 1 already done, Module 2 and 4 to be delivered later) | MetLife - Module 3 (Components of the the mobile app version and compatibility) | 1. StageCraft 2. Angelini Development project. 3. Assessment Module
2018-07-10 | 1. YardStick Testing 2. Community | 1. YardStick (Reveal Component) | MetLife Module 4 - Structure, Module 5 - Calculator | MetLife - Module 3 (Components of the the mobile app version and compatibility) | YardStick - Interactive Table component.
2018-07-11
2018-07-12
2018-07-13
2018-07-14
2018-07-15
2018-07-16
2018-07-17
2018-07-18
2018-07-19
2018-07-20
2018-07-21
2018-07-22
2018-07-23
2018-07-24
2018-07-25
2018-07-26
2018-07-27
2018-07-28
2018-07-29
2018-07-30
2018-07-31
2018-08-01
2018-08-02
2018-08-03
2018-08-04
2018-08-05
2018-08-06
2018-08-07
2018-08-08
2018-08-09
2018-08-10
2018-08-11
2018-08-12
2018-08-13
2018-08-14
2018-08-15
2018-08-16
2018-08-17
2018-08-18
2018-08-19
2018-08-20
2018-08-21
2018-08-22
2018-08-23
2018-08-24
2018-08-25
2018-08-26
2018-08-27
2018-08-28
2018-08-29
2018-08-30
2018-08-31

## Sept-Oct-Nov
Sr No | 1 | 2 | 3 | 4 | 5 | 6 | 7
Name | Chetan | Akshay | Amruta | Sarveshwar | Nayan | Rohidas | Rakesh
Date | Activity | Activity | Activity | Activity | Activity | Activity | Activity
2018-09-01
2018-09-02
2018-09-03
2018-09-04
2018-09-05
2018-09-06
2018-09-07
2018-09-08
2018-09-09
2018-09-10
2018-09-11
2018-09-12
2018-09-13
2018-09-14
2018-09-15
2018-09-16
2018-09-17
2018-09-18
2018-09-19
2018-09-20
2018-09-21
2018-09-22
2018-09-23
2018-09-24
2018-09-25
2018-09-26
2018-09-27
2018-09-28
2018-09-29
2018-09-30
2018-10-01
2018-10-02
2018-10-03
2018-10-04
2018-10-05
2018-10-06
2018-10-07
2018-10-08
2018-10-09
2018-10-10
2018-10-11
2018-10-12
2018-10-13
2018-10-14
2018-10-15
2018-10-16
2018-10-17
2018-10-18
2018-10-19
2018-10-20
2018-10-21
2018-10-22
2018-10-23
2018-10-24
2018-10-25
2018-10-26
2018-10-27
2018-10-28
2018-10-29
2018-10-30
2018-10-31
2018-11-01
2018-11-02
2018-11-03
2018-11-04
2018-11-05
2018-11-06
2018-11-07
2018-11-08
2018-11-09
2018-11-10
2018-11-11
2018-11-12
2018-11-13
2018-11-14
2018-11-15
2018-11-16
2018-11-17
2018-11-18
2018-11-19
2018-11-20
2018-11-21
2018-11-22
2018-11-23
2018-11-24
2018-11-25
2018-11-26
2018-11-27
2018-11-28
2018-11-29
2018-11-30